## Report
INTELLIGENT APPLICATION FOR DATA ANALYSIS | [11 empty] | Earned Value Analysis Report
| Prepared By: | Sai Maneesh Veerulla
| Date: | 30/04/2024
[42]
| For Period: | Week 1
Summary:
Purpose: Track project progress, budget, and performance indicators. Metrics: Planned Value (PV): Budgeted cost of work scheduled. Earned Value (EV): Value of work completed. Actual Cost (AC): Actual cost incurred. Cost Variance (CV): Difference between EV and AC. Schedule Variance (SV): Difference between EV and PV. Usage: Assess project performance, identify deviations, and make data-driven decisions to keep the project on track.
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Planning Phase | 8500 | 5000 | 500 | 3000
1.2 | Implementation Phase | 6400 |  | 200 | 1000 | 1200 | 4000
1.3 | Tracking Phase | 7600 |  |  | 800 | 2000 | 4000 | 800
1.4 | Analysis Phase | 4300 |  |  | 200 | 600 | 2000 | 1500
1.5 | Reporting Phase | 2700 |  |  |  |  | 700 | 500 | 1000 | 500
1.6 | Continuous Improvement | 8000 | [7 empty] | 1000 | 2000 | 1000 | 3000 | 1000
0
| Total Budgeted Cost | 37500 | 5000 | 700 | 5000 | 3800 | 10700 | 2800 | 1000 | 1500 | 2000 | 1000 | 3000 | 1000
|  | Cumulative Planned Value (PV) | 5000 | 5700 | 10700 | 14500 | 25200 | 28000 | 29000 | 30500 | 32500 | 33500 | 36500 | 37500
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 800 | 1950 | 4550 | 6550 | 10800 | 13600 | 14500
|  | Cumulative Earned Value (EV) | 1275 | 5850 | 12320 | 15380 | 18175 | 25975 | 32395
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 475 | 3900 | 7770 | 8830 | 7375 | 12375 | 17895 | - | - | - | - | -
|  | Schedule Variance (SV = EV - PV) | -3725 | 150 | 1620 | 880 | -7025 | -2025 | 3395 | - | - | - | - | -
|  | Cost Performance Index (CPI = EV/AC) | 1.5938 | 3 | 2.7077 | 2.3481 | 1.6829 | 1.9099 | 2.2341 | - | - | - | - | -
|  | Schedule Performance Index (SPI = EV/PV) | 0.255 | 1.0263 | 1.1514 | 1.0607 | 0.72123 | 0.92768 | 1.1171 | - | - | - | - | -
|  | Estimated Cost at Completion (EAC) | 23529.4118 | 12500 | 13849.4318 | 15970.4161 | 22283.3563 | 19634.2637 | 16784.9977 | - | - | - | - | -
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Planning Phase | 8500 | 15% | 50% | 100% | 100% | 100% | 100% | 100%
1.2 | Implementation Phase | 6400 |  | 25% | 30% | 60% | 75% | 90% | 100%
1.3 | Tracking Phase | 7600 |  |  | 25% | 40% | 50% | 100% | 100%
1.4 | Analysis Phase | 4300 |  |  |  |  | 25% | 80% | 90%
1.5 | Reporting Phase | 2700 | [5 empty] | 25% | 75%
1.6 | Continuous Improvement | 8000 | [6 empty] | 50%
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | 1275 | 5850 | 12320 | 15380 | 18175 | 25975 | 32395 | 0 | 0 | 0 | 0 | 0

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Planning Phase |  | Wk 1: 800; Wk 2: 250; Wk 3: 1500
1.2 | Implementation Phase |  | Wk 2: 900; Wk 3: 700; Wk 4: 1200; Wk 5: 1700
1.3 | Tracking Phase |  | Wk 3: 300; Wk 4: 300; Wk 5: 1250; Wk 6: 1500
1.4 | Analysis Phase |  | Wk 3: 100; Wk 4: 500; Wk 5: 900; Wk 6: 700; Wk 7: 400
1.5 | Reporting Phase |  | Wk 5: 400; Wk 6: 600; Wk 7: 500
1.6 | Continuous Improvement
- | -
- | -
- | -
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 800 | 1150 | 2600 | 2000 | 4250 | 2800 | 900 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 800 | 1950 | 4550 | 6550 | 10800 | 13600 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500